REQUEST FOR PROPOSAL
TIME SCHEDULE FOR THE RFP/PROCUREMENT PROCESS

Procurement No:	RFQ- 27-W003-21

### Time Schedule for the RFP/procurement process

The Procurement will follow the timeline below for this RFP. Any changes to this timeline will be posted on the Kiribati Public Procurement Web Portal (www.procurement.gov.ki/opentender) or sent directly to Tenderers who have been specifically invited to submit a Tender. Please note that the dates set forth in 6-11 are target dates and may be adjusted.

| Event | Responsible Party | Date and time, KST* |
| --- | --- | --- |
| - Launch and publication of RFP | Procuring Entity | 18th October 2021 |
| - Pre bid meeting (discussion with bidders) | MISE Procuring Entity | 25th October 2021 10.00 am Mise Boardroom |
| - Last date for questions about RFP | Tenderer | 1st November 2021 |
| - Last date for answers to questions and/or to amend the RFP | Procuring Entity | 8th November 2021 |
| - Last date for submission of Proposals | Tenderer | 12th November 2021 - 5pm |
| - Tender Opening | Procuring entity | 15th November 2021 |
| - Evaluation finalized | Procuring entity, and recommended ministries. | 24th November 2021 |
| - Award of Contract | Procuring Entity | Subject to CCAB Schedule probably in the end of November or early Dec. |
| - Complaints period for 14 days |  | 8th December 2021 |
| - Contract Terms and Conditions | Procuring Entity/Tenderer | 15th December 2021 |
| - Contract signing | Procuring Entity/Tenderer | 17th December 2021 |
| - Contract/Project start date | Tenderer | 20th December 2021 |

* Kiribati Standard Time (Tarawa Time) GMT+12 – Proposals or Questions, or parts thereof, delivered after the latest date and time for submission will not be opened or considered.

** The Procuring Entity may decide to give a presentation of the Terms of Reference

*** Presentation opportunity may be given, and if so, to qualified Tenderers only