REQUEST FOR PROPOSAL
TERMS OF REFERENCE FOR CONSULTING SERVICES
TEMPLATE FOR NARRATIVE PROPOSAL

Procurement No:	50-cs002-21

List of Documents

A.	Description of the Services	3

B.	Team Composition and Roles	13

C.	Time Schedule for Professional Personnel	14

D.	Schedule of Project Activities	15

E.	Consultancy Deliverables	16

F.	Technical and Knowledge Capability	17

G.	Curriculum Vitae (CV) for Proposed Professional Staff	19

H.	Tenderer’s References	20

I.	Technical Component	21

J.	Financial Component	22

Expenses	22

## Description of the Services

ALL DOCUMENTS PRODUCED BY THIS CONSULTANCY SHALL BE WRITTEN IN PLAIN ENGLISH

The Consultant shall prepare the documents and deliver the services described below. In doing so the Consultant shall consult with the Chief Executive Officer of the Public Utilities Board and the Team Leader of the Kiribati Utilities Reform Programme, and people they may nominate from time to time.

All documents shall use standard MS Formatting (including table and figure numbering) and text shall be in Calibri 11-point font.

Governance Handbook

- The term “Governance Handbook” is used to describe a suite of documents which shall be prepared and used to guide PUB Directors in the carrying their duties as a Board member in the proper and effective manner.

- The documents that shall be prepared as part of the Governance Handbook are as follows. In some cases, templates are also required.

  - Guidelines:

    - Role of Board

    - Operation of Board

    - Appointment, Remuneration and Performance of Directors

  - Toolkits

    - Recruitment and Selection of Directors

    - Induction of Directors

    - Reporting to Government

    - Recruitment of Chief Executive Officer

    - Conduct of Board Meetings

- The documents shall be concise and all extraneous material removed. They must be well written in plain English with correct grammar and punctuation. A document control system shall be included. The use of dot points is encouraged and flow charts and pictures shall be used to illustrate matters as appropriate. The documents must be produced in MS Word using standard MS Word formatting.

- The contents of each of the document/toolkit shall at least include the following.

| Topic/Format | Content |
| --- | --- |
| Role of Board Guideline | - Role of Public Utility - Role in Governance |
| Operation of Board Guideline | - Operation of Board - Obligations of Board - Obligations of Directors - Governance Standards - Internal Audits - Government Guarantees - Community Service Obligations - Financial and Non-Financial Delegations - Procurement of Goods and Services |
| Appointment, Remuneration and Performance of Directors Guideline | - Scope and Application - Limitations - Recruitment and Selection of Directors - Qualifications and Experience - Probity Checks and Declarations of Interests - Remuneration - Performance - Templates |
| Recruitment and Selection of Directors Toolkit | - Planning - Statutory Requirements - Roles - Appointments and Re-Appointments - Attraction - Selection Process - Approval and Appointment - Notification and Induction - Performance Assessment - Templates |
| Induction of Directors Toolkit | - Role and Operation of Board - Code of Conduct for Directors - Obligations - Values (Responsiveness, Integrity, Impartiality, Accountability, Respect, Leadership and Human Rights) - Management of PUB - Practise Financial Responsibility - Maintain and Enhance PUB’s Reputation - Act in Best Interests of PUB - Manage PUB’s Risk - Manage Conflicts of Interest and Duty - Maintain and Enhance PUB’s Relationship with Stakeholders - Conflict of Interest and Duty - Actual - Potential - Perceived - Direct Private Interests - Financial Private Interests - Indirect Private Interests - Non-Private Interests - Gifts - Hospitality - Donations - Declarations - Disclosures - Management of Conflicts - Templates |
| Reporting to Government Toolkit | - Statement of Intent - Annual Report - Half Yearly Report - Auditor General Audits (External Audits) - Community Service Obligations - Protected Information - Templates |
| Recruitment of Chief Executive Officer Toolkit | - Knowledge Requirements - Experience Requirements - Behavioural Requirements - Terms and Conditions (including Benefits) - Performance - Remuneration - References - Selection Panel |
| Conduct of Board Meetings Toolkit | - Appointment of Secretary - Meetings and Decisions - Attendance at Meetings - Notices - Annual Workplan - Agenda - Declaration of Interests - Apologies - Previous Minutes - CEO’s Report - Papers for Approval - Papers for Discussion - Papers for Noting - Other Business - Board Action List - Board Workplan - Chief Executive Officer Report - Papers - Minutes - Records - Action List - Decision List - Templates |

- The estimated time budget for the preparation of the documents is as follows.

| Item | Time Budget |
| --- | --- |
| Role of Board | 2 days |
| Operation of Board | 4 days |
| Appointment, Remuneration and Performance of Directors | 3 days |
| Recruitment and Selection of Directors | 3 days |
| Induction of Directors | 6 days |
| Reporting to Government | 2 days |
| Recruitment of Chief Executive Officer | 2 days |
| Conduct of Board Meetings | 5 days |
| Total | 27 days |

Draft Board Policies

- In consultation with the Chief Executive Officer the consultant shall prepare a number of draft policies for the subsequent endorsement of the Board and the adoption and use by the Public Utilities Board. The policies shall be suitable for the culture and operating environment experienced in Kiribati.

- The polices shall be high level and each policy shall not exceed four A4 pages in 11-point type. The policies shall be effective in directing and guiding the activities of behaviour of the PUB staff.

- The polices to be provided are as follows.

  - Employee Code of Conduct

  - Health and Wellbeing

  - Work/Life Balance

  - Performance Management and Development

  - Remuneration

  - Employment Conditions

  - Outside Employment

  - End of Employment

  - Diversity

  - Bullying and Harassment

  - Gifts, Benefits and Hospitality

- The draft policies shall be delivered in accordance with the Schedule and the consultant shall allow for one iteration in the preparation.

- The time budget for the preparation of the draft policies is estimated as follows.

| Customised Drafts | - Employee Code of Conduct - Health and Wellbeing - Work/Life Balance - Performance Management and Development - Remuneration - Employment Conditions - Outside Employment - End of Employment - Diversity - Bullying and Harassment - Gifts, Benefits and Hospitality 11 documents x 3 days each = 33 days |
| --- | --- |

Board Training Program

- The consultant shall deliver four virtual training sessions following the completion of the Board Handbook and within twelve weeks after that time, at times mutually suitable to both parties. The training sessions shall be at least two weeks apart and shall comprise the following topics.

  - Session 1: Role and Operation of Board (Role of Board, Operation of Board, Board Reporting to Government)

  - Session 2: Recruitment and Performance of Directors (Appointment, Remuneration and Performance of Directors, Recruitment and Selection of Directors and Recruitment of Chief Executive Office)

  - Session 3: Induction of Directors (Induction of Directors)

  - Session 4: Conduct of Board Meetings (Conduct of Board Meetings)

- The durations of Sessions 1, 2, 3 and 4 shall be 3 hours, 3 hours, 4 hours and 3 hours respectively.

- The consultant shall allow for up to ten people at each training session.

- The consultant shall provide suitably knowledgeable trainers experienced in training and presenting, and shall use PowerPoint slides to support the training. The training slide decks shall be provided to the training session participants in advance.

- The time budget for the training sessions is as follows.

| Training Session 1: Role and Operation of Board | Preparation: 3 days Delivery: 3 hours |
| --- | --- |
| Training Session 2: Recruitment and Performance of Directors | Preparation: 3 days Delivery: 3 hours |
| Training Session 3: Induction of Directors | Preparation: 4 days Delivery: 4 hours |
| Training Session 4: Conduct of Board Meetings | Preparation: 4 days Delivery: 4 hours |

Board Mentoring and Advisory Service

- The consultant shall provide a Board Mentoring and Advisory Service over a 12-month period in the following manner.

  - The consultant shall undertake one-on-one sessions with the Chairman, the Directors and the Chief Executive Office. The number of sessions shall be four, three and six per person for each group respectively. There shall be at least one month between each session, and the sessions shall be held virtually.

  - The consultant shall ensure its mentors have a good understanding of Public Boards and their operations, a good understanding of the PUB and its operations, a good understanding of the existing capacity of PUB Directors, and a good understanding of Kiribati and the context within which the Directors work and live.

  - The mentors will share their knowledge, skills and life experiences with the mentees, guide the mentees towards becoming and effective Board members and act as a sounding board for mentee issues and concerns. The mentors shall ask questions and encourage mentees to look at issues from a variety of perspectives and focus on problem-solving, decision-making, and solutions. The mentors shall challenge traditional ways of thinking and encourage strategies outside of their mentee’s comfort zone.

  - The content of each mentoring session shall be strictly confidential and shall not be discussed in any manner with any other person nor documented in any way. The consultant shall not report on mentee performance.

  - The consultant may use a number of mentors to provide this service but shall ensure that the mentor/mentee relationship is sound, consistent and productive in each case.

  - The consultant shall attend (virtually) three Board meetings over a twelve-month period as selected by the Chief Executive Officer as an observer. The consultant shall not particulate in the meeting and shall only answer questions that are related to the conduct of the meeting or the procedures used. After each meeting the consultant shall prepare a report on its observations and shall submit this report to the Chairman and Chief Executive Officer within one week after the meeting.

- The consultant shall provide a responsive Board Advisory Service for a period of twelve months in the following manner.

  - The consultant shall allow for four hours of consultations to be undertaken each month for twelve months and shall accept and conduct consultations on a first-come-first-served basis until the monthly budget is exhausted. The consultant shall keep the consultations brief and on topic.

  - The consultant shall arrange for a common email address to be used for the purpose of arranging consultations and shall respond to a request for a consultation and complete the consultation within 36 hours of receiving the request for consultation. The consultant shall conduct the consultation using Zoom or WhatsApp.

  - The content of each consultation shall be strictly confidential and not be discussed in any manner with any other person nor documented in any way.

- The time budget for the Mentoring and Advisory Service is as follows.

| Item | Time Budget |
| --- | --- |
| Mentoring and Advice | Mentoring: 4 x 1-hour sessions: 1 Chairperson 3 x 1-hour sessions: 4 Directors 6 x 1-hour sessions: Chief Executive Officer 3 x 8-hour sessions: Review three Board packs and attend (virtually) as an observer three Board meetings and provide a report on observations and opportunities for improvement. Advising: 12 x 4-hour allowances: Monthly responsive advisory service Total: 94 hours |

Board Risk and Audit Committee

- The Consultant shall prepare the terms of reference (roles and responsibilities, composition, structure, memberships requirements, authority and procedures) for a Board Risk and Audit Committee and shall provide training to the Board on the operation of the Committee and the exercising of its authority. The Risk and Audit Committee shall at least address the following.

  - The management of PUB’s risks and risk register and to satisfy itself that the risks are being appropriately managed

  - Incidents resulting from a breakdown of the PUB’s internal controls are appropriately addressed

  - The PUB is carrying adequate insurance

  - The Committee’s reporting requirements

  - The attendance of non-members including the Chief Executive Officer, the Financial Controller and the Authority Secretary

- The budget for the Board Risk and Audit Committee is as follows.

| Item | Time Budget |
| --- | --- |
| Terms of Reference | 3 days |
| Consultation | 2 days |
| Committee Charter | 2 days |
| Training | 3 days |
| Total | 10 days |

Milestones

- The consultant shall deliver the materials and services in accordance with the following.

| Item | Completion from Commencement |
| --- | --- |
| Board Handbook | by 10 weeks |
| Board Policies | by 20 weeks |
| Board Training | from weeks 11 to 36 |
| Mentoring and Advice | from weeks 21 to 72 |
| Audit Committee | by 20 weeks |

Payment

- The consultant shall be paid a percentage of its lump sum fee upon the acceptance of the consultant’s documents or the delivery of its services and the submission of a suitable completion invoice in accordance with the following table.

| Document | Pay |
| --- | --- |
| Board Handbook (paid on acceptance) | 27.98% |
| Board Policies (paid on acceptance) | 34% |
| Board Training (paid per session) | 4 x 4% |
| Mentoring (paid per month whether used or not) Board Meetings (paid per meeting whether used or not) Advising (paid per month whether used or not) | 22 x 0.11% 3 x 0.8% 12 x 0.6% |
| Board Risk and Audit Committee | 10% |
| Total | 100% |

Timetable

## Team Composition and Roles

The Consultant shall nominate the people it intends to use in undertaking the Consultancy and shall complete this form accordingly as part of its proposal. Please make sure the Curriculum Vitae proposed people cover the various items of the Assignment listed in the ToR.

| Consultants (also see G. Curriculum Vitae) |  |  |
| --- | --- | --- |
| Name | Position | Role |

## Time Schedule for Professional Personnel

Not applicable.

## Schedule of Project Activities

Not applicable.

| ## Consultancy Deliverables The Consultant shall meet the following dates for deliverables. |  |
| --- | --- |
| Output | Time from Contract Effective Date |
| Governance Handbook | By 10 Weeks |
| Draft Board Policies | By 20 Weeks |
| Board Capacity Building Program | Weeks 11 to 36 |
| Board Risk and Audit Committee | Weeks 11 to 72 |
| Audit Committee | By 20 Weeks |

## Technical and Knowledge Capability

The Tenderer must demonstrate is has the technical knowledge and capability using the forms as follows:

- Track Record

- Capability Statement (includes curriculum vitae of proposed staff)

- Capacity Statement

- Proposed Solution

| A. Track Record |  |
| --- | --- |
| - Describe what experience the firm has in delivering the services required under this contract |  |
| Answer: |  |
| - Describe any specific experience which is relevant to this opportunity i.e., local conditions and environmental factors. |  |
| Answer: |  |
| - Provide two examples of previous/current projects which demonstrate the ability to meet the Requirements of this contract. Include: - a brief description of the scope of services performed (including the key service areas, and any ancillary services you provided) - a brief description of how the delivery of the services to the client was managed - a brief commentary of the quality and timeliness of the services |  |
| Answer: |  |

| B. Capability |  |
| --- | --- |
| - List the people who will deliver the services, and their qualifications and experience (including any Biographies). Describe how many staff will be allocated to the contract, and also describe how this may change and be managed throughout the delivery of the Requirements. Include the CVs of proposed staff. |  |
| Answer: |  |
| - Describe how you ensure your staff develop and maintain a high skill set in the delivery of the services required under the contract |  |
| Answer: |  |

| C. Capacity |  |
| --- | --- |
| - Describe your organisation’s track record in delivering similar services (same quantity, quality, delivered on time, to specification and within budget). |  |
| Answer: |  |
| - Describe how you will interact with key stakeholders in the delivery of the services. |  |
| Answer: |  |
| - Describe your organisation’s size, structure and annual turnover. Explain why this is sufficient to deliver the services in full, on time, to specification and in the quantity required. |  |
| Answer: |  |

| D. Proposed Solution |  |
| --- | --- |
| - Explain how your services meet or exceed our Requirements |  |
| Answer: |  |
| - Describe how you measure quality in meeting or exceeding our Requirements |  |
| Answer: |  |
| - Provide a workplan tailored to the delivery of the services |  |
| Answer: |  |
| - Describe how the training will be delivered and how this will relate to the documents to be produced |  |
| Answer: |  |
| - Provide the curriculum vitae of the people whom shall undertake the work |  |

The Technical Component shall not include any information regarding the Financial Proposal.

## Curriculum Vitae (CV) for Proposed Professional Staff

The Consultant shall provide CVs of all people nominated in B. Team Composition using the following format as part of its proposal.

| CURRICULUM VITAE FOR INTERNATIONAL SPECIALIST |  |  |
| --- | --- | --- |
| Personal Details |  |  |
| Position: |  |  |
| Name of Firm: |  |  |
| Name of Specialist: |  |  |
| Country of Residency: |  |  |
| Email: |  |  |
| Mobile Contact Number: |  |  |
| Education: |  |  |
| Memberships of Professional Associations: |  |  |
| Countries with In-Country Work Experience: |  |  |
| Language(s) and Proficiency: |  |  |
| Employment Record: | From: | To: |
|  | Employer: |  |
|  | Position(s) Held: |  |
|  | Repeat for Employment |  |
| Employment Relevant to the Assignment |  |  |
| Name of Assignment: |  |  |
| Year(s): |  |  |
| Location: |  |  |
| Client: |  |  |
| Project Description: |  |  |
| Position Held: |  |  |
| Duties Undertaken: |  |  |
|  | Repeat for each Assignment |  |
| Certification |  |  |
| This CV is an accurate record of my Employment: | Y/N |  |
| Signature: | Date: |  |

## Tenderer’s References

## Technical Component

The Technical Component comprises the experience of the firm (Technical and Knowledge Capability) and the experience of the proposed personnel (Curriculum Vitae). These shall be scored as follows:

- Track Record – 10 points

- Capability Statement (includes curriculum vitae of proposed staff) – 40 points

- Capacity Statement – 20 points

- Proposed Solution – 30 points

## Financial Component

The Tenderer shall submit its Financial Proposal in the following form:

In preparing the Financial Component, Tenderers are expected to take into account the requirements and conditions outlined in the RFP documents.

| E. Price |  |
| --- | --- |
| Provide the fixed price (excluding Expenses as listed below). The price must be entered in Australian Dollars (AUD). |  |
| Answer: |  |

### Expenses

Should travel to Kiribati be required the Consultant shall be paid/reimbursed the following per person (maximum one trip for two people).

- Return airfare: AUD3,000

- Accommodation: AUD120 per day for nights away from home country

- Per Diem AUD40 per day for nights away from home country

- One off payment of AUD250 per person

- A work permit will be obtained and paid for by FCG

No other expenses shall be paid.

Expenses do not from part of the Financial Component Evaluation.

No taxes or charges are payable in Kiribati. No other payments will be made.