REQUEST FOR APPLICATION
TERMS OF REFERENCE FOR CONSULTING SERVICES
PROCURING ENTITY REQUIREMENTS

Procurement No:	16-CS003-21

List of Documents

A.	About the Ministry	3

B.	Project Background and Objectives	3

C.	Service Requirements	3

Suggested methodology	3

Competence requirements and allocation	3

Environmental and Social considerations	3

D.	Timetable and Reporting Arrangements	3

Submission of Deliverables	3

Reporting Arrangements	4

## About the Ministry

The Ministry of Environment, Lands & Agricultural Development (MELAD) work portfolio is organised into four key areas, i) Policy and Management Unit (PMU), ii) Environment Conservation Division (ECD), iii) Land Management Division (LMD) and iv) Agriculture and Livestock Division (ALD). All these four divisions are respectively managing the environment and biodiversity conservation, customary and state lands and agriculture and livestock development initiatives in Kiribati. The ECD, LMD and ALD through their respective branch offices extended their management outreach to Kiritimati island and all the islands in the Line and Phoenix group. MELAD also houses the Phoenix Islands Protected Area (PIPA) office whose main responsibility is to implement protection and conservation management initiatives on the 8 islands of the Phoenix group.

The Ministry of Line and Phoenix Islands Development (MLPID) is the key implementing partner and support Ministry whose core function is to coordinate all administrative, development and project activities implemented on Kiritimati Island including other islands in the Line and Phoenix group. The ECD through its branch office in Kiritimati, the Wildlife and Conservation Unit – WCU, focuses on wildlife conservation, protection, and management of the 9 protected areas (PAs) and wildlife sanctuaries on the island. WCU is also administratively answerable to the MLPID.

## Project Background and Objectives

The Biodiversity and Protected Areas Management (BIOPAMA) programme is providing support to the Government of Kiribati through a 30 months Kiritimati Island Conservation Protected Areas project to develop a Management Plan whose primary focus is to enhance and improve effective management and governance of conservation and protected areas in Kiritimati Island.  The project is financially supported by the Organization of ACP group of States and the EUand managed by IUCN through the BIOPAMA programme.

The objective of the project is to improve the sustainable management of the 9 protected areas on Kiritimati. The three-key priority actions that the project and its activities will address includes; enhancing the management and governance of priority protected areas on Kiritimati through the implementation of the management plan which will address existing limitations, strengthening on site infrastructure/equipment for patrolling, poaching control and developing staff capacities. The project will also assist to strengthen the enforcement and effective implementation of existing legal frameworks required for effective biodiversity conservation and will support local community initiatives and awareness programs aiming to enhance the livelihood of the local people whilst effectively contributing to protected areas management.

One of the main activities of the project is to hire an environmental specialist and consultant (TA) to develop and produce a management plan which will not only be the key to achieving the overall outcome of the project but will also ensure fulfilling of BIOPAMA objectives.

The complete and approve management plan will be used and implemented by local communities, stakeholders, government agencies and including foreigners who are on the Island as tourists. The hired International consultant (TA), will be expected to travel to Kiritimati Island to carry out the assignment for the duration of the contract. TheTA will be base and work at the Wildlife Conservation Unit (WCU) Office in Ronton, Kiritimati Island  and expected to work closely with the Officer in Charge (OIC) for WCU and staff.  This arrangement is based on the expected opening of borders and resumption of international flights in January 2022.

## Service Requirements (TOR)

The main responsibility of the TA is to develop a management plan and to ensure the public is aware of the plan and whoever may be responsible to enforce, implement and monitor this plan. Provision of related training and capacity developments is another key undertaking of the hired TA.

Listed below are specific activities the TA shall undertake and accomplish within the term of the contract with the assistance of WCU staff.  When travel restrictions are lifted in January 2022 the hired international TA shall take responsible steps to make appropriate travel arrangements to Kiritimati to carry out the assignment required. Travel expenses will be reimbursed upon production of appropriate travel documents and receipts.

- The selected individual shall develop and produce a management plan for the protected areas in Kiritimati and other required documents and reports within the given time frame and working in close consultation with the project implementing office WCU in Ronton Kiritimati and ECD office in Tarawa.

- Conduct consultations to communities, stakeholders and the public for awareness of the management plan in terms of its importance, coverage, institution and regulatory frameworks and set of rules and procedures to comply once the management plan is endorsed.

- Offer the required training for the implementation of the management plan to WCU staff, and other relevant stakeholders on the Island.

- Build technical capacity of WCU staff and other relevant stakeholders on the importance and effective methods for wildlife in particular seabirds conservation, habitat survey and analysis, data collection and monitoring.

### Suggested methodology

- The selected candidate shall produce a detailed workplan, setting out activities and timelines within the contract term that shall include but not limited to i) community and stakeholder consultations, ii) list of wildlife conservation related trainings, iii) documentation of training materials and mid-term progress reporting, iv) compilation, stakeholder review and submission of final draft of management plan,

- The detailed workplan and activities shall consider effective approaches and methodologies under the current pandemic circumstances and promote knowledge transfer to WCU staff..

- The management plan shall consist but not limited to a section(s) on patrolling for illegal poaching, bird monitoring, data collection and conservation practices, invasive species controls, habitat surveys and rehabilitation measures addressing effects of climate change and other human induced activities

### Competence requirements and allocation

To be verified by the Applicant with a relevant CV and certificates

The successful applicant shall meet the following minimum criteria;

Education:

- Minimum of advance Master’s Degree in fields related to environment conservation, particular focus on wildlife and seabirds conservation and management OR any other related environment fields

Experience:

- Proven track record and experience in the area of conservation, preference for wildlife seabirds conservation or related environmental fields

- Minimum of 5 years’ experience in the field of environment conservation or related disciplines and practices

- Proven past experience in consulting works and development of a management plan and capacity development and training

- Ability to render consulting services in the most professional, effective and efficient manner.  Strong networking, good interaction and influencing skills is required.

### Environmental and Social considerations

The analysis and derived outputs produced in the context of this consultancy shall consider environmental and social requirements and how they will be addressed. Please, refer to the Certificate of Compliance Form included in this RFP.

To be specified by the Tenderer in the ‘Terms of Reference Narrative’ Template included in this RFP

## Timetable and Reporting Arrangements

### Submission of Deliverable

Specific dates will be agreed in the Contract.

| Deliverable No. | Deliverables | Timeline (from project start date) |
| --- | --- | --- |
| 1 | Submission of work plan and inception report on methodology to develop management plan MP | 2 weeks after signing and commencement of contract - due date 5 days after |
| 2 | Submission of 1st Draft of MP | End of first 40 days- due date 7 days after |
| 3 | Submission of report for staff training and community and stakeholder awareness of the MP | End of 50 days – due date 7 days after |
| 4 | Submission of 2nd draft MP | End of 60 days - due date 7 days after. |
| 5 | Submission of final draft MP with review and inputs from the national stakeholder workshop incorporated | End of the 70 days contract – due date 10 days after. |

### Reporting Arrangements

- The TA work progress will be monitored through daily consultations with the implementing office WCU and the ECD through verbal and email communications, however the consultant shall submit formal updates and briefing reports any time when so required.

- During the review and approval process for the final draft of the Management Plan the consultant shall be contacted for the comments and clarifications from  stakeholder and Cabinet regarding the contents and context of the Management Plan. The Consultant shall consider, respond in writing and where necessary make inclusion or amends to the Management Plan.

Example:

The Consultants work progress will be monitored primarily through monthly review meetings/calls, the precise schedule of which is to be determined based on consultation with the Consultant. The Consultant is also expected to produce, upon request, a formal progress report to the Contract Manager and Project Manager that includes: an overview of the project, a narrative description of project activities, detailed information on project objectives and milestones, actual achievements made against the timeline initially set, etc.